## Task List
Tasks | Scheduled | Completed | Prelim Budget | Comments
Whole Team
Clean 601A Rhodes |  |  | - | Continuous Process
Keep updating System Breakdown |  |  | - | Continuous Process
Update WBS and SBS |  |  | - | Continuous Process
Fundraising
Gulfstream Aerospace |  | 2013-09-21 | -
Belcan | 2013-09-26 |  | - | Haven't heard back from them yet
Kinetic Vision | 2013-09-26 | 2013-10-01 | -
TECT Power | 2013-09-26 | 2013-10-01 | -
Foxlite |  | 2013-09-01 | -
Triumph Thermal Systems | 2013-09-26 |  | -
-
-
Structures
Landing Gear
Fuselage Design
Main Wing Ribs
Front Spar Design | 2013-10-22 | 2013-11-25
Front Spar Analysis | 2013-10-24 | 2013-11-25
HT and VT Ribs
Aileron Ribs
Elevator Ribs
Rudder Ribs
Motor Mount/Nose Design
Aerodynamics
Main Wing Airfoil Section |  | 2013-09-07 |  | S1223_TC
HT & VT Airfoil Section | 2013-10-02 | 2013-11-14
Wing planform | 2013-10-02 | 2013-09-21
Trailing Edge | 2013-10-02 | 2013-11-14
Leading Edge | 2013-10-02 | 2013-11-14
SnC
Aileron design | 2013-10-09 | 2013-11-14
Aileron Hinges | 2013-10-09 | 2013-11-14
HT Tail Placement | 2013-10-02 | 2013-11-14
Rudder Design | 2013-10-09 | 2013-11-14
Elevator Design | 2013-10-09 | 2013-11-14
Servo Selection | 2013-12-05
Propulsion
Motor/prop combination | 2013-10-02 | 2013-11-14
Batteries | 2013-10-02 | 2013-11-14
Safety Shunt | 2013-10-02 | 2013-11-14
Electric Control System | 2013-10-02 | 2013-11-14
Limiter |  | 2013-11-25
Safety Spinner | 2013-10-02
Performance
Ground Roll trade study | 2013-10-02 | 2013-11-14
Wing size trade study | 2013-10-02 | 2013-11-14
Wing size drag trade study | 2013-10-02 | 2013-11-14
Ground roll vs span | 2013-10-02 | 2013-11-14
Flight Ops